## #Stores
Stores
Sr. No | Heading |  | Problem areas | problems with link
1 | Enquiry | Create | Product description is not displayed what we have added in the product master. |  | Completed
|  |  | print option not available |  | It is not required
|  |  | RFQ link working | Aliignment needs to be done, letterhead format is not correct, RFQ heading is missing.
|  |  |  | RFQ by email should not go automatically the email window should pop up and there should be an option to edit the text. | Not Possible
|  |  |  | Also when it sends email system should give option to send email to various contacts mentioned in customer/ supplier master, and cc options for team memebers | Completed | Pls explain
|  |  |  | Product description is not displayed what we have added in the product master. | Completed
|  |  | Store customer offer link | The link is working but not able to submit ( Notification select product , although the product is selected. | Completed
2 | Store customer offer |  | print option not available |  | Already Done. Pl chk after approval
|  |  | Product description is not displayed what we have added in the product master. |  | Completed | In print the product description is not visible
|  |  | No link for Order Confirmation |  | Completed
3 | Order |  | Quotation selection option is not working |  | its working
|  |  | Email link is missing |  | Completed | link is not working
|  |  | print working just small corrction required | In case of customer address we dont wanrt the sate field to be dispalyed. | Completed | Still not corrected
|  |  | Product description is not displayed what we have added in the product master. | Also we need the colum Sr. No. When we are entering the data. This coloum is available in print. | Completed | Not Working
|  |  | Remarks are not dispalyed in the print | also in remarks there should be an option to add seperate remark in seperate line | Completed | Not Working
|  |  | Discount is not counted on total aswell as individual item wise. | we need one more coloum as discount and it should calculate the discount itemwise | Completed
|  |  | Schedule link is working |  | Working
|  |  | Shipment link is not working | sales person is not carried forwward and there is no option to selct . So not able to save. | Completed
|  |  | Invoice liknk is missing | for some options we might create invoice without shedule / shipment | Not Possible
4 | Schedule |  | Shipment link not working |  | Completed
|  |  | packing list link not available |  | Completed
|  |  | UPS link missing |  | Completed
|  |  | when order is proceeded to schedule/shipment sales person is not always transfered |  | Completed
5 | Shipment |  | print format is not correct |  | Completed
|  |  | print is not taking all fields eg. Vehicle no mode of transport delivery from- to |  |  | Not Working
|  |  | the heading should be despatch details currently ist despatch. |  |  | Not Yet changed
link to packing list not available
|  |  | email option is required. |  | Completed
|  |  | when order is proceeded to schedule/shipment sales person is not always transfered |  | Completed
6 | Packing list |  | Packing list format is not correct the existing format is for the trading format. |  | Pl provide the correct format | packing list previously what you have given that format only we did. this new format will be in the next version
|  |  | ups link not available |  | OK TBD
|  |  | When we select the order no ist not extracting the data from order we have to enter the |  | WE been told earlier that data to be entered only
7 | Invoice |  | discount is not calculated |  | Completed | Very critical still not working
|  |  | The payment term field is not available |  | Completed
|  |  | when we select the order it is showing multiple entries for same product but when we print ist correct. |  | Completed
|  |  | email link is not available. |  | Completed
|  |  | It should allow entry for new Item other than order confirmation |  | Not Possible | It is must
|  |  | Certificate of entry link is not available |  | OK TBD
Invoice cancelation option should be possible.
8 | Supplier offer |  | Ist displaying all suppliers offeres. | showing all the supplier offers. It should only show supplier offers relevant for stores only. | Completed
create
|  |  | working good. | need Print and email option | OK TBD
9 | Supplier PO |  | list display |  | fixed
|  | create | not saveing - undefined error |  | fixed
|  |  | No product names in drop down list |  | fixed
|  |  | no search function in all Pos overview |  | fixed
10 | Supplier Price list
|  |  | takes about 30 seconds to load article list |  | To be checked
|  |  | no Row-Numbers shown | if product is repeated it is telling which row - to find out you have to count. Wasteing time | OK TBD
|  |  | Products are not sortet as per product group | If you want to change prices for specific article searching is very difficult | OK TBD
11 | GoodsInward |  | In overview more Colums required (e.g. Date, PO etc.) |  | OK TBD
In selectin Products article
12 | Transfer |  | working
* Sr No. Colum to put in all formats.