## 22ndApril
Requirements | Development
New requirements in PO:
Another category "CLOSED" to be added in the "PO STATUS" and it should display If all the Qty in that particular PO received. | Yet to Develop
Need a provision to add a product in-between in the Product Grid. | Yet to Develop
Existing Errors in PO:
Add "Currency" after "total(order value)" in the purchase order front page. - Meenatchi please refer the image which i have sent in whats-app for the PO changes. I have clearly mentioned. | Need to check
Every-time when i add a product in the grid, the page takes more time to refresh & also goes to Top position and each time i have to scroll down and add the product. This makes my work delay. Kindly fix the error. - Still not resolved. | R & D
In "Revision Note" need Cursor moving option within the cell, even-though the above line is not fully typed. | R & D
Print PO report should exactly match the sample PO format shared to you(again i have attached to this mail). Make sure the alignment & color also looks the same. the words highlighted in red color is just to show which data should come there, but actual data will be in Black color only. Also whichever currency is selected, the report should have same currency wherever applicable. | Yet to Develop
Supplier Pending PO's:
Default View should have PO number, PO Date, Supplier Name, Article number, Item Code, Item Description, Finish, Uom, PO Qty, Pending Qty. | Completed
Add Filter option for "PO" to search for a particular PO. | Completed
Add Export options like Excel, Pdf etc same as in product master. | Yet to Develop
Supplier Deliveries:
Default View should have PO number, PO Date, Supplier Name, Article number, Item Code, Item Description, Finish, Uom, G.I no, G.I Date, PO Qty, G.I Qty. | Completed
Add Filter option for "PO" to search for a particular PO. | Completed
Add Export options like Excel, Pdf etc same as in product master. | Yet to Develop
Supplier Price List:
The default view should be Supplier Code, Supplier Name, Active Status, Active from & Actions. Note each supplier should be listed only once in the front page. | Completed
Inside each supplier we have to create list of products which we are buying from them. Add Currency tab. Remove the export option(excel, pdf, csv & Copy) in the front page and incorporate in the inner page(ie "Create Supplier Price List" page). | Yet to Develop
Need a provision to add multiple number of products under each supplier even after it is submitted(ie: in edit option), so that we can add new products in future. | Yet to Develop
The default view of product grid in the "Create supplier List" should have Article Number, Product Code, Description, Finish, Uom, Unit Price. | Yet to Develop
Unit price should be linked from "Product Master" and is automatically populated. | Yet to Develop
Currency should also be included during export report. | Yet to Develop
Add "Factor" tab which will have same feature as in PO page. eg: if the factor is 0.8 & unit price for that particular product is 10 from "Product Master" then, the Unit price should be displayed as 0.8 x 10 = 8. | Yet to Develop
Currency & Factor should be inter-Linked, ie: when i select the currency the corresponding factor will automatically display. Note the Standard Factors for Currency, USD-0.8, GBP-0.611, AED-3.088, Euro-0.712, INR- 56.00. | Yet to Develop
Supplier Setup:
Default view should have Supplier Code, Supplier Name, Supplier Type, Company Status, Country, Website & Actions. | Completed
Add Proprietor Name, Import Code & VAT Reg in filter option. | Completed
Reports - Procurement:
ADD Excel export option for all report | Yet to Develop
When you select a particular supplier in any report, the "Choose PO" filter option should show only the PO reference corresponding to that particular supplier. but now it is displaying all the PO's. | Completed
Time Period filter option not working properly, In Custom date option drop down list overlaps with date dialog box & the date filter is also not working properly. | yet to Develop
PO Register:
Default view should have PO date, PO number, Rev#, Supplier Name, Article Number, Item Code, Description, Finish, Uom, PO Qty, GI Date, GI number, Received Qty. | Completed
After filtering the particular PO, the same item code is repeated many times with the same GI reference. eg: If a material received for a particular PO at different intervals, then it will have different GI reference. Please fix this error & check the filter option work properly. | Yet to Develop
The heading(ie: sl.no, PO.no, PO date etc...) in the PDF report should repeat in each page. | yet to Develop
Supplier Price List:
Default report view should be Supplier Name, Article Number, Item Code, Description, Finish, UOM, Unit Price, Currency. | Completed
The heading(ie: sl.no, PO.no, PO date etc...) in the PDF report should repeat in each page. | Yet to Develop
PO Pending register:
Default report view should be PO number, PO Date, Supplier name, Article Number, Item Code, Description, Finish, UOM, PO Qty, Pending Qty. | Completed
The heading(ie: sl.no, PO.no, PO date etc...) in the PDF report should repeat in each page. | Yet to Develop
PO Cancellation register:
Default report view should be PO number, PO Date, Supplier name, Article Number, Item Code, Description, Finish, UOM, PO Qty, Cancellation Date. | Completed
The heading(ie: sl.no, PO.no, PO date etc...) in the PDF report should repeat in each page. | Yet to Develop

## 28thApril
Requirement | Development
Product Master:
Remove all suggestions in "Create" page during new article number creation. | Yet to Develope
During "Import", the software does not show the correct number of duplicate errors(refer the attachment in which i have created one new record and kept 9 old records and imported. In this scenario system should show 9 duplicate records but shows only 3 and the one new record is added. Also shows "There is no row at position 0" in green color. I have attached the file which i used for checking. please cross check. | Need to check
Store:
Whatever changes made in the Product master it should reflect in the Store. Eg: If an item deleted in product master, same item should be deleted in Store also(refer ZDL7255 in store which is repeated twice because of this error), even if i change any data of particular product, same should reflect in store. | Yet to Develope
If i change the opening stock & Opening stock date in product master, that qty should become the current stock in store from that date it changed and then qty will be added or reduced as per upcoming G.I & Dispatch from that date. Also the date filter will also have effect due to this correction. we will discuss this over phone and close. | Need to check
If any G.I or Dispatch is cancelled then it should reflect on the store qty. | Yet to Develope
Goods Inward:
If any G.I is cancelled, the PO & that particular Qty should reverse back and we should be able to reuse it. Eg: If PO/000027/2019 has ZHSS43 - 100nos and 1st G.I is raised for 50nos and balance 50nos will be pending. then 2nd G.I is raised for 50nos for the same PO. but the Qty received only 30nos. so i have to cancel that G.I and raise a new G.I for 30nos. In this case i must be able to reuse the PO. Hope you understand. Please revert if you don't. | Yet to Develope
Purchase Order no. search option in drop down list not working. | Need to check
Commercial Invoice date not showing in the Edit page as well as front page after i submit the G.I. Please fix the error. | Need to check
Replacement from supplier & Customer's return need to be explained and discuss the requirement | Need to check
REPORTS - INVENTORY:
Add Excel export option for all the reports. | Yet to Develope
Inventory Summary:
Please explain "Inventory Summary" report and the purpose of that. Right now nothing is displayed. | Need to check
Receipt Register:
Change the name from "Receipt Register" to "G.I Register" | Yet to Develope
Default view should be Sl.no, G.I Date, G.I no. G.I type, Supplier name, PO ref, Article Number, Item Code, Item Description, UOM, finish, G.I Qty, Com.Invoice no & Com.Invoice Date. | Yet to Develope
Remove "Item Type" filter and add "Supplier" & "Time Period"(same as PO register) filter. | Yet to Develope
Under "Supplier" filter add "G.I Type" & "Choose G.I" filter. | Yet to Develope
Make sure after filtering the particular "supplier", the "G.I type" should show the corresponding types available for that particular "supplier" & then after choosing a particular "G.I Type", the "choose G.I" should show only the corresponding "G.I no". | Yet to Develope
ROL Items:
This report should display only the items that reaches the ROL level. | Yet to Develope
The default view should be Article no, Item Code, Item Description, Base Material, Brand, finish, UOM, Current Stock, ROL Level. | Yet to Develope

## Completed
Module | Form | Date | Requirement
Administrator | Company Setup | 2019-01-01 | Added the company logo and stamp atachments
|  | 2019-01-01 | Multiple bank details added
|  | 2019-01-01 | Added the feature for attachments(5 attachments added)
added the fields newly Proprietor,Address,Tel,Email Id,Website ,Type: Individual/Partnership
| User Setup | 2019-01-01 | Signature image uplodaing added
CRM | CustomerSetup | 2018-12-01 | the fields newly added - the fields are Proprietor Name,Website ,Payment Terms,Delivery Terms,Dispatch Terms,Import Code,inclusions,Validity of offer
|  | 2018-12-01 | multiple contact person details added
|  | 2018-12-01 | Added the feature for attachments(2 attachments added)
Inventry | Product Code master | 2019-01-01 | newly one form added for listing the product code
| Product Master | 2019-01-01 | new concept generate for article no Article No Generation 97.05.001.549.01 First digit for-Brand Second digit for-category Third digit for-productCode fourth digit for-base material fifth digit for-finish
|  | 2019-01-01 | new fields added for generating the article no(base material,brand,finish)
|  | 2019-01-01 | some more field added(Weight/Piece,Carton Size(CM),HS Code,Country of Origin)
|  | 2019-01-01 | Added the feature for attachments(5 attachments added)
| Store product | 2019-03-01 | showed the each product qty
|  | 2019-03-01 | displayed the total qty of all product
|  | 2019-03-01 | displayed the total qty*weight of all product
|  | 2019-03-01 | displayed the total value of all product
|  | 2019-03-01 | date wise product filter added
| GI | 2019-02-02 | Commerical invoice no and invoice date field added
|  | 2019-02-02 | Added the feature for attachments(2 attachments added)
|  | 2019-02-02 | added the new popup for selecting the item,based on product code
|  | 2019-02-02 | po can use upto all the qty received for that po
Procurement | Supplier setup | 2019-01-01 | the fields newly added - the fields are Proprietor Name,Website ,Payment Terms,Delivery Terms,Dispatch Terms,Import Code,inclusions,VAT number,validity of offer
|  | 2019-01-01 | multiple contact person details added
|  | 2019-01-01 | Added the feature for attachments(2 attachments added)
Freight Forwarder: added fields - Company Name,Proprietor,Address,Country,Tel,Email Id,Website Link,bank account details
| Purchase order | 2019-01-01 | the fields newly added - the fields are Project Ref,Rev# ,Revision Note,Factor,Currency
|  | 2019-03-02 | Revision note should display in print format
|  | 2019-01-03 | the same popup implemented for selecting the item
|  | 2019-01-04 | Based on the currency the naming should differ in print format
calendar |  | 2018-12-01 | Fields are Appointment with alert,Trans.no,Company name,Location,Meeting with whom,Meeting Date,Time,Purpose,Conclusion,Status: Inprogress, Completed , Cancelled